## Slide 1
External Team Meetings | Length | Cadence | Agenda
ART Sync | 60 minutes | Once a sprint (Last Monday) | Give a high level Product status to stake holders for all the Artifacts identified during PI Planning.
Scrum of Scrums | 30 minutes | Once a week (Thursday) Closer to testing sprints, twice a week (Tuesday and Thursday) | Track dependencies on all line items on the Integration Tracker from Testing/Release point of view based on due dates.
CloudEagles/DevOps Dependency Call | 30 minutes | Once a week (Friday) | Discuss all new dependencies with DevOps team and follow up on existing dependencies.
Sprint Review/Demo | 210 minutes | Once a sprint (Last Tuesday) | Demo all features and functionalities completed in the sprint
DevOps Connect | 30 minutes | Twice a week (Tuesday and Thursday) | TA’s and DevOps connect for all technical discussions
Internal Team Meetings | Length | Cadence | Agenda
Daily Scrum | 15 minutes | Daily | Sprint Task Status, Blockers
Refinements | 60 – 90 minutes | Twice a week (Tuesday and Thursday)/As needed. | Groom User stories/Scope
Sprint Retrospective | 60 minutes | Once a sprint (Last Tuesday) | What went well/bad in the sprint & Ideas for future
Sprint Planning | Upto 360 minutes | Once a sprint (First Wednesday) | Planning scope for new sprint

## Slide 2
Iteration # | Start Date | Finish Date | Release Date | PI Planning
81 - 1 | Mar 31, 2021 | Apr 20, 2021 |  | 
82 - 2 | Apr 21, 2021 | May 11, 2021 |  | 
83 - 3 | May 12, 2021 | June 1, 2021 |  | 
84 – Testing | June 2, 2021 | June 22, 2021 |  | 
85 - IP | June 23, 2021 | July 13, 2021 | July 17, 2021 (Audit Online & DAD) July 13 (AQMM) | PI 6 - July 13 - 15, 2021
86 – 1 | July 14, 2021 | Aug 3, 2021 |  | 
87 – 2 | Aug 4, 2021 | Aug 24, 2021 |  | 
88 – 3 | Aug 25, 2021 | Sep 14, 2021 |  | 
89 - 4 | Sep 15, 2021 | Oct 5, 2021 | (EMS) | 
90 – Testing | Oct 6, 2021 | Oct 26, 2021 |  | 
91 – IP | Oct 27, 2021 | Nov 16, 2021 | Nov 13, 2021 (Audit Online & DAD), | PI 7 - Nov 9 – 11, 2021
92 – 1 | Nov 17, 2021 | Dec 7, 2021 |  | 
93 – 2 | Dec 8, 2021 | Dec 28, 2021 |  | 
94 – 3 | Dec 29, 2021 | Jan 18, 2022 |  | 
95 – 4 | Jan 19, 2022 | Feb 8, 2022 |  | 
96 – 5 | Feb 9, 2022 | Mar 1, 2022 |  | 
97 – IP | Mar 2, 2022 | Mar 22, 2022 | Mar 19 (Audit Online, DER & DAD) | PI 8 - Mar 15 – 17, 2022
Audit Transformations: PI Cadence & Release Dates

## Slide 3
Iteration # | Start Date | Finish Date | Release Date | PI Planning
98 - 1 | Mar 23, 2022 | Apr 12, 2022 |  | 
99 - 2 | Apr 13, 2022 | May 3, 2022 |  | 
100 - 3 | May 4, 2022 | May 24, 2022 |  | 
101 – 4 ½ testing | May 25, 2022 | June 14, 2022 | June 6 – 14, Mid Release Testing | 
102 - 5 | June 15, 2022 | July 5, 2022 |  | 
103 – 6 | July 6, 2022 | July 26, 2022 |  | 
104 – 7 – ½ testing | July 27, 2022 | Aug 16, 2022 |  | 
105 – Testing | Aug 17, 2022 | Sep 6, 2022 | UAT – Aug 22 – 26, 2022 | 
106 - IP | Sep 7, 2022 | Sep 27, 2022 | Sep 17, 2022 | PI 9 – Sep 20 – 22, 2022
107 -1 | Sep 28, 2022 | Oct 18, 2022 |  | 
108 – 2 | Oct 19, 2022 | Nov 8, 2022 |  | 
109 – 3 | Nov 9, 2022 | Nov 28, 2022 |  | 
110 – 4 1/2 testing | Nov 29, 2022 | Dec 20, 2022 | Dec 12 – 20, Mid Release Testing | 
111 – 5 | Dec 21, 2022 | Jan 10, 2023 |  | 
112 – 6 | Jan 11, 2023 | Jan 31, 2023 |  | 
113 – 7 – ½ testing | Feb 1, 2023 | Feb 21, 2023 |  | 
114 – Testing | Feb 22, 2023 | Mar 14, 2023 | UAT Mar 6 – 10, 2023 | 
115 – IP | Mar 15, 2023 | Apr 4, 2023 | March 25, 2023 | PI 10 – Mar 28 – 30. 2023
Audit Transformations: PI Cadence & Release Dates

## Slide 4
Iteration # | Start Date | Finish Date | Release Date | PI Planning
116 – 1 | Apr 5, 2023 | Apr 25, 2023 |  | 
117 – 2 | Apr 26, 2023 | May 16, 2023 |  | 
118 – 3 | May 17, 2023 | June 6, 2023 |  | 
119 – 4 ½ testing | June 7, 2023 | June 27, 2023 |  | 
120 – 5 | June 28, 2023 | July 18, 2023 |  | 
121 - 6 | July 19, 2023 | Aug 8, 2023 |  | 
122 – 7 – ½ testing | Aug 9, 2023 | Aug 29, 2023 |  | 
123 – Testing | Aug 29, 2023 | Sep 19, 2023 | Sept 10 | 
124 – IP | Sep 20, 2023 | Oct 10, 2023 | Sep 30, 2023 | PI 11 - Oct 3 – 4, 2023 (Oct 2 will be USI holiday)
Audit Transformations: PI Cadence & Release Dates

## Slide 5: PI6 Milestones *
Start: July 14, 2021
  Official Start: July 16, 2021
4 Development Sprints
  First Sprint – 3 weeks
  Second Sprint – 3 weeks
  Third sprint – 3 weeks
  Fourth Sprint should allow for buffer – 1.5 weeks for those releasing in November
  RC 1 (Bronze) Code Freeze: Sep 24, 2021; only P1/P2 defects post
Regression, Performance, Backward Compatibility, China, Integration, PEN – Start Sep 27, 2021
RC 2 (Silver) Code Freeze: 8 October, 2021; only showstoppers P1 post
UAT – Week of 11 October 2021
Gold Code: 29 Oct 2021; Gold Code=Ready for Staging
Production Deployment:
  Nov 13 for AO
Innovation Sprint: Sprint 91; begins 27 October 2021
PI Planning for Nov PI: (Nov 9 - 11, 2021)
Start next release on Nov 17 (March 2022 release)
*This is for products releasing around end of PI. For those not releasing in November, your Code Freeze dates and UAT may differ. Please confirm with your SM/DL/TL for schedule.

## Slide 6
Sprint 80
Testing (Regression, China, Backward, Integration, Performance) and Critical Defects
Technical Deployment
Sprint 81
PI Planning - 5
AO Deploy
AO Start
Gold Code
Final UAT
Ad Hoc Testing/Buffer

## Slide 7
Sprint 82
ER Deploy
AQMM Deploy
CMS Deploy

## Slide 8
Sprint 83
US Holiday
USI – Holiday
Testing (Regression, China, Backward, Integration, Performance) and Critical Defects
AO Code Freeze

## Slide 9
Sprint 84
Sprint 85
Testing (Regression, China, Backward, Integration, Performance) and Critical Defects
Testing (Regression, China, Backward, Integration, Performance) and Critical Defects
Tech Deployment
Final UAT
AO Gold Code
USI – Holiday
Testing (Regression, China, Backward, Integration, Performance) and Critical Defects
Ad Hoc Testing/Buffer
Testing complete

## Slide 10
Sprint 86
Tech Deployment
PI Planning - 6
US Holiday
AO/DAD Deploy
AO Start
AO/ER Code Package
AQMM Deploy
US Holiday

## Slide 11
Sprint 87
Sprint 88
BCP POC Testing

## Slide 12
Sprint 89
US Holiday
USI – Holiday
AO Code Freeze
Testing (Regression, China, Backward, Integration, Performance) and Critical Defects
AO Bronze Code
Iconfirm Build
BCP Password Rotation Testing

## Slide 13
Sprint 90
Sprint 91
Testing (Regression, China, Backward, Integration, Performance) and Critical Defects
Final UAT
Testing (Regression, China, Backward, Integration, Performance) and Critical Defects
AO Gold Code
USI – Holiday
Testing (Regression, China, Backward, Integration, Performance) and Critical Defects
AD Hoc Testing/Buffer
AO Silver Code
ER Deploy
Pen Testing
Pen Testing
Pen Testing
Pen Testing

## Slide 14
Sprint 92
Tech Deployment
PI Planning - 7
US Holiday
AO /DAD Deploy
AO Start
USI – Holiday
AQMM Deploy

## Slide 15
Sprint 93
Sprint 94
US/USI - Holiday
Password Rotation Testing

## Slide 16
US Holiday
USI – Holiday
USI – Holiday
Sprint 95
AO Code Freeze

## Slide 17
Sprint 96
Testing (Regression, China, Backward, Integration, Performance) and Critical Defects
Final UAT
Testing (Regression, China, Backward, Integration, Performance) and Critical Defects
Ad Hoc Testing/Buffer
Testing (Regression, China, Backward, Integration, Performance) and Critical Defects
Testing (Regression, China, Backward, Integration, Performance) and Critical Defects

## Slide 18
Sprint 97
Sprint 98 - 1
Ad Hoc testing/Buffer
Technical Deployment
Gold Code
PI Planning - 8
AO/ER/DAD Deploy
AO Start
AQMM/ENS Deploy

## Slide 19
USI – Holiday
Sprint 99 - 2

## Slide 20
USI – Holiday
US Holiday
Sprint 100 - 3
Sprint 101 – 4 – ½ Testing

## Slide 21
USI – Holiday
Sprint 102 - 5
Gold Code
Mid Release Testing
Mid Release Testing

## Slide 22
US Holiday
Sprint 103 - 6
Sprint 104 – 7 – ½ Testing

## Slide 23
USI – Holiday
USI – Holiday
USI – Holiday
Sprint 105 - Testing
Final UAT
Testing (Regression, China, Backward, Integration, Performance) and Critical Defects
Testing (Regression, China, Backward, Integration, Performance) and Critical Defects
Testing (Regression, China, Backward, Integration, Performance) and Critical Defects
Testing (Regression, China, Backward, Integration, Performance) and Critical Defects
AO Code Freeze

## Slide 24
US Holiday
Sprint 106 - IP
Sprint 107 - 1
AO Deploy
AO Start
PI Planning - 9
Technical Deployment
Ad Hoc/Buffer
Testing (Regression, China, Backward, Integration, Performance) and Critical Defects
AO Gold Code
Test Complete

## Slide 25
USI – Holiday
USI – Holiday
Sprint 108 - 2

## Slide 26
US Holiday
Sprint 109 - 3
Sprint 110 – 4 -1/2 Testing

## Slide 27
US/USI - Holiday
Sprint 111 - 5
AO Code Freeze
Mid Release Testing
Mid Release Testing

## Slide 28
Sprint 112 - 6
US Holiday

## Slide 29
Sprint 113 –7-½- Testing
Sprint 114 - Testing
Testing (Regression, China, Backward, Integration, Performance) and Critical Defects
Testing (Regression, China, Backward, Integration, Performance) and Critical Defects
Testing (Regression, China, Backward, Integration, Performance) and Critical Defects
AO Code Freeze

## Slide 30
Sprint 115 - IP
PI Planning – 10
AO Deploy
Technical Deployment
Ad Hoc/Buffer
Test Complete
Testing (Regression, China, Backward, Integration, Performance) and Critical Defects
Final UAT
AO Gold Code
Testing (Regression, China, Backward, Integration, Performance) and Critical Defects

## Slide 31
Sprint 115 - IP
AO Start
Sprint 116 - 1