## Pre-Work
S.No | Item | Assigned To | Comments | Status
1 | New webjob: EMSOnlineDataValidation-ArchiveOnPremRequestCleanUp | devops | Same schedule as EMSOnlineDataValidation-RequestCleanUp Add to Installation Manual
2 | truncate and run the ActivityTrigram table | ema devops | This task wil be needed with all new columns - in dacpac release
3 | rebuild for trigram table (confirm for China) | ema devops
4 | Configure IConfirm AppID and update in infra pipeline (STG) | devops
5 | Infrastructure definition update for APA, EMA, AME Production | ema/apa/ame devops | user identity for encrypted key vault for WFO
6 | Code definition update for APA, EMA, AME Production | ema/apa/ame devops
7 | verify Stats/Index/Index-Large (Runbook pipeline) | devops
8 | Database definition update for APA, EMA, AME Production | ema/apa/ame devops
9 | Backward compatibility archive zip files 5.1 |  |  | up to date
10 | Raise RFC for Production | Vanessa | AO 1. RFC for EMA for WFO and AO 3. RFC for APA for WFO 4. RFC for AME for WFO | EMA: CHG0174568 APA: CHG0174570 AME: CHG0174572
11 | Advance notice to EMA AME and APA DevOps team | Vanessa | AO SG-US Audit DevOps EMA <usauditdevopsema@deloitte.com>; SG-US Audit DevOps APA <usauditdevopsapa@deloitte.com>; SG-US Audit DevOps AME <usauditdevopsame@deloitte.com>
12 | Advance notice to MF - Arif (STG & PRD) | Arif | comunication to MF (10 days prior) | done
13 | Communication to Content team on deployment dates (PRD) | discuss | stop publish | done
14 | Email to seek approval for production deployment. | Vanessa | day before release
15 | Meeting invites for Staging and Production deployment | Lauren | nov. 1st: stg, sems9 - 5.2, lrn - 5.3 | staging: done, production: done
16 | L10 Translation file | Dev Team (Vyshnavi) | four hours before deployment
17 | EMSOnline 5.2 Release Testing | QA team
18 | PowerBI - BI Reports |  | send notification to Allie once deployment is completed check powerBI
20 | create meeting with member firms to explain changes |  | send out week before release
21 | Data setup for testing | QA team
Enable Secrets-(TP-P):Azure PowerShell script: FilePath task in Rotate Secrets

## Key_Dates_Time
Audit Online - Staging - SEMS9 (5.2), LRN (5.1) - November 1st
S.No | Item | Assigned To | Start Time | Duration
0 | L10 Translation file | Dev Team (Vyshnavi) | 4 hours before
0 | Verify Stats/Index/Index-Large (Runbook) is running in PRD | DevOps | Done |  | We do not have runbooks in STG
0 | add AD group for testing (day before) | Lauren | Day Before
0 | Run Infa deployment | Devops | Day Before
1 | Switch traffic manager to Maintenance Page | DevOps | 6:00AM EST |  | https://dev.azure.com/symphonyvsts/EMSOnline/_build?definitionId=9408&_a=summary
2 | Stops apps and webjobs | DevOps | 6:05AM EST |  | https://dev.azure.com/symphonyvsts/EMSOnline/_build?definitionId=9408&_a=summary
7 | Run database definition - WFO and AO | EMA, AME, APA DevOps | 6:10 AM - 6:40 AM
8 | Truncate Trigram in dacpac | EMA DevOps | 6:10 AM - 6:40 AM
9 | Rebuild trigram in dacpac | EMA DevOps | 6:10 AM - 6:40 AM
10 | Run code definition - WFO and AO | EMA, AME, APA DevOps | 6:30 AM - 7:00 AM
11 | Run ADF Pipeline | EMA DevOps | 6:30 AM - 7:00 AM
12 | Start apps and webjobs | DevOps
13 | Switch traffic manager to AO | DevOps
14 | Test AO (BC) | QA Team | 8:00AM EST
15 | Upgrade SEMS9 (5.2), LRN (5.1) | DevOps Team
16 | Test AO - 5.2 + WFO | QA Team
17 | Test concludes | QA Team
Audit Online - TP, Production & BCP - TP4 (5.2), GP4 (5.2) - November 13th [Included SQL Passwword Rotation]
S.No | Item | Assigned To | Start Time | Duration
1 | Run Maintenance Page | EMA DevOps
2 | Stops apps and webjobs (WFC and WFO) | EMA DevOps
3 | Run Infra in WFC and WFO (EMA, APA, AME) | EMA, AME, APA DevOps |  |  | PCBP - APA failed
4 | Remove subnet westeurope_staticvnetsubnet (PRD) northeurope_staticvnetsubnet PBCP | EMA DevOps
5 | remove aaps-emsonline-kv-pb (PBCP) | EMA DevOps
6 | Run database definition - AO and WFO | EMA, AME, APA DevOps
7 | Truncate Trigram in dacpac | EMA DevOps
8 | Rebuild trigram in dacpac | EMA DevOps |  |  | NOTE from AO5.2 deployment: When rebuilding trigram, ensure that flag 0 is changed to 1
9 | Deploy ADF Code | EMA DevOps
10 | Run code definition - WFO and AO | EMA, AME, APA DevOps
11 | Run OSS Pipeline | EMA DevOps
12 | Password Rotation -- Rotate SQLAdmin, ReadOnlyDBUser, DBUser | EMA, AME, APA DevOps |  |  | Not part of normal software deployment
13 | Test AO (BC) GP4 | QA Team
14 | Upgrade GP4 | DevOps Team
15 | Verify ADF and DataValidation schedules | DevOps Team
16 | Test AO - 5.2 (test Omnia, Levvia and IConfirm) | QA Team |  |  | Noted in AO5.2 deployment that Save GRA to EMS, Save document to EMS and WP Transition processing was halted. Naveen disabled scheduled tasks on primary and changed to secondary and that allowed the processing to succeed.
17 | Test concludes | QA Team
18 | Update PowerBI Passwords | EMA DevOps
19 | Power BI refresh existing reports | EMA DevOps
20 | Send out concluding email (Include Allie and Arnold) | DevOps
Note:
Add in APA cert deletation and run