## AATRM milestones
Audit Online v5.2 Deployment Date 11/13/2021 | Tranche | Status | Preparer | Reviewer | Target Completion Date | Product Team Review | Portofilo Leader Review (Craig) | TC Manager Review (Vanessa) | TC Manager Review (Hesham) | Cyber Security (Peter) | TC Sr Manager Review (Ryan) | TC Leader Review (Chris) | COAT Review | ARM review | A&A Review | Comments | Leadership review date
Demand ID |  | Complete | Dharini | Mythili/Jyothsna
Onboard in AATRM |  | Complete | Dharini | Mythili/Jyothsna | [11 empty] | Do not onboard until previous release has been archived so that data can rollover.
Release scope and design | 1 | [15 empty] | Go live | 2021-07-17
Summary of changes |  | Complete | Lauren |  | 2021-10-04 | ü |  | ü | x | x | x |  | n/a | x | x | Once BCP is complete, Summary of Changes will complete | MTP | 2021-07-17
Proposed Architecture Review & Approval - Document |  | Complete | Jignesh | Mythili P | 2021-10-07 | [7 empty] | n/a | x | x | Before Bronze Code Freeze. Changes in Diagrams and No changes in the Architecture Structure. Cyber assessment document gets uploaded here. Document submitted to Cyber team. Meeting on Oct 4, 2021. Uploaded Revised document. - Michelle to approve. | Tranche | TC Leader | COATs
Processing Environment |  | Not applicable | [6 empty] | x | x |  |  | n/a | x | x |  | Tranche 1
Business and Functional Requirements |  | Complete | Lauren | NA | Sprint 89/Sept 17 (after sprint planning) | ü |  |  | x | x |  |  | n/a | x | x | Query: 22852 Audit Online>AO Requirements and Regression>AO5.2 Backlog (Epic-Feature-PBI). Vanessa to close once reviewed. | Tranche 2
Stakeholder Biographies |  | Complete | Dharini | Mythili/Jyothsna | Start | ü |  | ü | x | x |  |  | n/a | x | x |  | Tranche 3
High level PAR - Deck |  | Complete | Jignesh | Mythili P | 2021-10-07 | [7 empty] | n/a | x | x | Upload to MF Repo. Uploaded in the AATRM Portal. Michelle & Vanessa to approve
Product Risk Assessment | 1
Tailoring Questions |  | Complete | Lauren |  | 2021-08-20 | ü |  | ü |  | x |  |  | n/a | n/a | x | ARM review not required given it is a semi-major. Vanessa to review the PBI's | Legend
Data Risks |  | Complete | Lauren |  | 2021-08-20 | ü |  | ü |  |  |  |  | n/a | n/a | x | Added DCRM control under Data Risks- Data Collection>'PII, PHI, and/or other CI collected (which is necessary to the functionality of the Application) may not be properly safeguarded.' and Kangatong malware fix under Data Risks - Data Storage (Application data is susceptible to a cyber attack.) | Reviewed | ü
Data Collection |  | Complete | Lauren |  | 2021-08-20 | ü |  | ü |  |  |  |  | n/a | n/a | x |  | Reviewed - Discreationary | üD
Data Storage |  | Complete | Lauren |  | 2021-08-20 | ü |  | ü |  |  |  |  | n/a | n/a | x |  | Pending | [ ]
Data use |  | Complete | Lauren |  | 2021-08-20 | ü |  | ü |  |  |  |  | n/a | n/a | x |  | Approval required in AATRM
Operational Risks |  | Complete | Lauren |  | 2021-08-20 | ü |  | ü |  | x |  |  | n/a | n/a | x |  | Not Applicable | x
Expertise and resource constraints |  | Complete | Lauren |  | 2021-08-20 | ü |  | ü |  | x |  |  | n/a | n/a | x |  | Limited procedures relying upon TC Advisory / Cyber Security for full review. My review and sign-off within the AATRM Portal consisted of a cursory review of Slide 2 (Document Control Information) and Slide 4 (Business Summary).
Performance and support |  | Complete | Lauren |  | 2021-08-20 | ü |  | ü |  | x |  |  | n/a | n/a | x
User adoption and experience |  | Complete | Lauren |  | 2021-08-20 | ü |  | ü |  | x |  |  | n/a | n/a | x
Regulatory Risks |  | Complete | Lauren |  | 2021-08-20 | ü |  | ü |  | x |  |  | n/a | n/a | x
Contractual |  | Complete | Lauren |  | 2021-08-20 | ü |  | ü |  | x |  |  | n/a | n/a | x
Independance |  | Complete | Lauren |  | 2021-08-20 | ü |  | ü |  | x |  |  | n/a | n/a | x
Policies and standards |  | Complete | Lauren |  | 2021-08-20 | ü |  | ü |  | x |  |  | n/a | n/a | x
Product documentation | 2
Understanding the Product |  | Complete | Lauren |  | No Changes | ü |  | ü | x | x |  |  | n/a | x | x | No Change
Audit Objectives and Audit Methodology |  | Complete | Lauren | Tania Sergott | Complete |  |  |  | x | x |  |  | n/a | x |  | With Vanessa T
Key Assumptions and Limitations |  | Complete | Lauren |  | Complete | ü |  | ü | x | x |  |  | n/a | x | x | Added GRAPA Python upgrade Limitation to the limitations area (8/27/20)
Operating Model |  | Complete | Lauren |  | Complete | ü |  | D | x | x |  |  | n/a | x | x
Change Management |  | Complete | Lauren | Q/Aoife (GRA/WP) Reese Frame (RADC) | Connect with Learning |  |  |  | x | x |  |  | n/a | x | x | No Change/Email sent to Learning by Lauren. Lauren to add response here.
User Support |  | Complete | Dharini | Mythili | 2021-09-03 | ü |  | D | x | x |  |  | n/a | x | x | No Change/The document is in the portal for review.
Product Testing | 2
Product Testing Strategy |  | Complete | Lauren |  | 2021-10-07 |  |  |  | x | x |  |  | n/a | x | x | This is drafted. GRAPA testing was removed as we cannot test this with latest Python upgrade and limitation added in AATRM. Need to update the deployment table as we are closer to deployment in case new member firms onboard.
Performance Testing |  | Complete | Lauren | Arnold | after Silver Code 10/22/2021 |  |  | D | x | x |  |  | n/a | x | x | Once Performance is complete. Lauren will review results and document. Arnold will review the summary document. and Arnold will review the summary. 11/8/21: Awaiting WP Transition updates (Message sent to Usha/Vijaya)
Quality Assurance Testing |  | Complete | Rachel/Ramana | Lauren | 2021-10-29 |  |  | D | x | x |  |  | n/a | x | x | Query: 22852 Audit Online>AO Requirements and Regression> Ensure all have test cases Update Parent column to be area (RADC, GRA, WP Transition) Add Outcome column for test case of Pass/Fail Each Fail should have coresponding Defect if Open; if closed, then pass. In active work for queries cleanup. Initial document uploaded
Business Validation Testing |  | Complete | Lauren |  |  |  |  | D | x | x |  |  | n/a | x | x | There is no separate Business Validation Testing for Audit Online. Business Validation Testing is performed as each Member Firm onboards the product after Audit Online deployment and prior to their deployment to Production.
User Acceptance Testing |  | Complete | Bhavita/Zois | Lauren | After Silver Code; 10/22/2021 |  |  | D | x | x |  |  | n/a | x | x | Data Preparation is in Progress.
Regression Testing |  | Complete | Rachel/Ramana | Lauren | 2021-10-29 |  |  | D | x | x |  |  | n/a | x | x | Query: 22852 Audit Online>AO Requirements and Regression>AO5.2 Regression Testing Coverage_PBI- Test Case Update Parent column to be area (RADC, GRA, WP Transition) Remove Assigned To on PBIs;keep on test cases Add Outcome Table with Pass/Fail Each Fail should have coresponding Defect if Open; if closed, then pass. In active work for queries cleanup. Initial document uploaded
Core Functionality and Workflow Validation |  | Complete | Geedha/Rachel | Lauren | 2021-10-26 |  |  | D | x | x |  |  | n/a | x | x | Only test GRA CMS>AO>EMS>AO
Defects and Disposition |  | Complete | Zois/Manohar | Lauren | By Final Go/No-Go; 11/8/2021 |  |  |  | x | x |  |  | n/a | x | x | Query: 22852 Audit Online>Open Defects_Audit Online_Defer Update Parent to be area (RADC, GRA, WP Transition) Based on Created Date, highlight items from previous release.
Tester Biographies |  | Complete | Rachel/Ramana | Mythili/Jyothsna | 2021-10-29 |  |  | D | x | x |  |  | n/a | x | x | All PBI and Regression testers, inc Dev. Uploading is complete. Connected to Regression queries cleanup
Security Matrix Considerations_RADC_ADC In the Portal it is one section |  | Complete | Ramana/Padmini | Lauren | 2021-10-26 |  |  |  |  | x |  |  | n/a | x | x | Calendar and EP Task Upload. Lauren to check with Padmini
Security Matrix Considerations_RADC_OST In the Portal it is one section |  | Complete | Rachel/Geedha | Lauren | 2021-10-26 |  |  |  |  | x |  |  | n/a | x | x | No Changes. Rachel to upload to Release folder in Teams
Business Continuity Plan and Testing |  | Complete | Vanessa/Naveen | Jignesh/Anubha | 2021-10-02 |  |  |  | x | x |  |  | n/a | x | x | Approved by Vanessa. Waiting for Documentation Approvals. Approval email included in the document.
Legal | 2
Third Party Considerations |  | Complete | Mythili |  | 2021-09-25 |  |  |  | x | x |  |  |  | x | x | Vanessa to send document on how to add entry - Complete Shabab/Mythili to add a TPRM entry/use case for Audit Online under Kanini for Waseem and Mark. For March: Also need to create an entry in TPRM for the APEX vendor. This is for September onwards. Once added, please make Vanessa and Taseen aware.
Open Source Software (Whitesource)/PDF in the Notices Pop-up |  | Complete | Jignesh |  | After Gold Code; 11/10/2021 |  |  |  | x | x |  |  |  | x | x | Mythili to Follow up to understand the process. Two notices (Front and Back-end) 1. Validate & update project list 2. Run the scan pipeline 3. Email Robert Frasier (OGC: Office of General Counsel), cc security, TC that scans are ready 4. They will provide 2 pdfs 5. We have to park the pdfs at _______ <Janine to follow up on this with AO teams (dev, devops) - there is a PBI to change the location - maintain outside of source code and separate pipeline to place them in the appropriate location> If OGC has questions, see Janine's previous email on how this scenario was handled OGC gets backed up.
Data Retention Considerations |  | Complete | Lauren |  | 2021-09-24 |  |  |  | x | x |  |  |  | x | x | Entity Fields, ID to link to Levvia and Inactive flag on non-Levvia; member firm to delivery center team mapping
Front End & Back End Notices/Link to Docs Files |  | Complete | Jignesh |  | After Gold Code - 10/29/2021 | n/a | n/a | n/a | x | x | n/a | n/a | x | x | x | Per confirmation with Vanessa(16 Sept), this is part of Notices so will be updated as part of Notice update.
Privacy Statement (Part of Notices) |  | Complete | Jignesh |  | After Gold Code - 10/29/2021 | n/a | n/a | n/a | x | x | n/a | n/a | x | x | x | Vanessa to provide the updated link for privacy notices and Teams to update the copyright to the link of Privacy notices.
Code Copyright |  | Not applicable | TA's to understand process |  |  | n/a | n/a | n/a | x | x | n/a | n/a | x | x | x | Connect on process; n/a for semi-major release. Schedule a KT for TA's from Janine
Security | 2
Code scan - Contrast (DAST) |  | Complete | Jignesh | Michelle/Peter | Final report right after Gold Code; 10/29/2021 |  |  | D | [7 empty] | Contrast is ongoing o Q and notifies Jignesh and Janine. Mythili: How do I get added to the notification? How does it get added to the sprint backlog or defect fixes? Levvia implemented the contrast automation. Agents are the contrast agent - we have one for every app service we have. We download and install agents on q. We monitor the routes. Levvia could add new agents to find something new at any time and this can kick off a high issue right before release. Can we disable new agent capability between gold code and new PI?
Code scan - Veracode (SAST) Pre-Run |  | Complete | Jignesh | Michelle/Peter | 2021-10-26 |  |  | D | [7 empty] | Connect on Process; Do a prerun to give us time for remediation
Code scan - Veracode (SAST) Final run |  | Complete | Jignesh | Michelle/Peter | Final report right after Gold Code; 10/29/2021 |  |  | D | [7 empty] | Connect on Process; After Gold code freeze. This is a devops pipeline. Jignesh can run it. Report comes out in 2 hours.
Penetration Test Scheduling |  | Complete | Jignesh | Brian | Schedule post PI planning once uat date is known - |  |  | D | [5 empty] | x | x | Janine requested for scheduling. Typically, Zois/Ramana does a demo but test occurs in USI time therefore need USI support. AO November release key dates: 9/24: Initial code freeze 9/27-10/8: Regression Testing (first two weeks) 10/11-10/15: UAT - START PEN TEST ON 10/11 10/11-10/22: Regression Testing (final two weeks) 10/29: AO Gold Code 11/1-11/5: Stage Deployment 11/13: Prod Deployment Request sent; Brian reviewing; no confirmation yet Set up U2 Env for Penn Testing by Oct 6, 2021(DevOps activity - PBI # 1666531) 9/9 - Scoping meeting scheduled. Meeting on 9/17
Penetration Test Execution - Internal |  | Complete | Jignesh | Michelle/Peter | End Date 10/25/2021 Retest - 11/01/2021 |  |  | D | [5 empty] | x | x | Have to do this in 2021 even though this is semi-major and does not need pen test however since we did not have pen test last year, we have to do it now -Synopsis -Internal Retest planned for High findings
SSL |  | Complete | Jignesh |  | Once deployed to Staging; 11/5/2021 | [8 empty] | x | x | On Gold Code. In Staging
Cyber Assessment & Review | 2
Cyber Design Review (PAR) |  | Complete | Jignesh | Lee Kelly, Bobby: bomazumder@deloitte.com | 2021-10-07 | [10 empty] | Connect on Process; New portal - only answer filling out is incorrect. Need to do this for 5.1. New assessment request for each release when PAR is ready.Completed for 5.1 and have to create a new request for 5.2. Signoff and document uploaded to PAR section in AATRM. New Request for 5.2 is created and the PAR document will be uploaded to Cyber Assessment Portal by EOD 9/23 Documents uploaded to portal and meeting on Monday Oct 4, 2021
Control Evaluations | 2
Testing Considerations |  | Complete | Ryan |  |  |  |  | x |  | x |  |  |  | x | x | Hesham will completed that section in the portal before we go live.
Testing Conclusion and Evidence |  | Not applicable | Hesham |  | NA in this release |  |  | x |  | x |  |  |  | x | x | Remanining Activity - Verification of Annual GITC Findings. Sep 18, 2021
Closeout & Archive | 3
Stakeholder Signoff |  | Not applicable | Lauren |  | n/a | n/a | n/a | n/a | n/a | x | n/a | n/a | n/a | x | n/a
Governance Committee Deck |  | Not applicable | Chris / Vanessa |  | n/a | n/a | n/a | n/a | n/a | x | n/a | n/a | n/a | x | n/a | n/a
Governance Committee Approvals |  | Not applicable | Chris / Vanessa |  | n/a | n/a | n/a | n/a | n/a | x | n/a | n/a | n/a | x | n/a | n/a
Go-live approval call |  | Complete | Dharini | Mythili/Jyothsna | 2021-11-08 |  |  |  |  | x |  |  |  | x |  | Pre Go/No-Go on Oct 28, 2021 Need to have deck updated; usually send reminder week before Pre-Go/No-Go (Audit Online > Release Readiness > Readiness Decks) https://teams.microsoft.com/_#/files/Release%20Readiness?threadId=19%3A90fe168e0f314be8816bec34d920d009%40thread.skype&ctx=channel&context=Readiness%2520Decks&rootfolder=%252Fsites%252FEMSOnline%252FShared%2520Documents%252FRelease%2520Readiness%252FReadiness%2520Decks
Post Deployment Activities | N/A
Project/Release Archive |  | Not Started | Vanessa |  | Post Deployment/ Nov 13, 2021 |  |  |  |  | x |  |  |  | x
Update Member Firm Repository |  | Not Started | Vanessa |  | Post Deployment/ Nov 13, 2021 | n/a | n/a | n/a | n/a | x | n/a | n/a | n/a | x | n/a

## Status
Not Started | STATUS | Mandatory | Required
In Progress |  | n/a
Delayed |  | If applicable
In Review with TC Mgr
In Review with TC Sr Mgr
In Review with Product Owner
In Review with TC Leader
In Review with Cyber
In Review with ARM
In Review with OGC
In Review with A&A Services
In Review with Product Leader
Ready for National Office
In Review with National Office
Review notes to be addressed
Complete
Not applicable

## Information
Add NewUser Name:
If the user’s name is not available in the system, here is link to ServiceNow request form to add users to AATRM portal: AATRM Request ¦ Deloitte US (service-now.com)
https://deloitteus.service-now.com/aatrm/
Submit request for that person
Choose you want Role Assignment
Select Product Team Lead group (they combined Product Team and Team lead into one group)